## Data Engineering Plan
Serial No. | Target Action | Category | Start Date | End Date | Target Actions / Scope | Free Resource Links | Paid Resource Links | Expected Output / Deliverable | Completion Criteria / Evaluation | Planned Hours | Actual Completion Date | Actual Hours Spent | Status | Progress % | Blockers / Notes | Course Correction / Feedback Needed
1 | SQL diagnostic and core SQL refresh | Practice Prep | 26-05-2026 | 28-05-2026 | Baseline test: SELECT, JOIN, GROUP BY, HAVING, CASE, CTE. Identify weak areas before deeper prep. | https://leetcode.com/studyplan/top-sql-50/ ¦ https://mode.com/sql-tutorial/ |  | Baseline SQL notes and weak-area list | Solve 10 mixed SQL questions with >80% accuracy |  | 30-05-2026 |  | Completed | 100
2 | Advanced SQL practice: joins, windows, CTEs | Practice Prep | 29-05-2026 | 08-06-2026 | Daily SQL practice: joins, window functions, CTEs, date logic, aggregation, ranking, cohort-style queries. | https://leetcode.com/studyplan/top-sql-50/ ¦ https://mode.com/sql-tutorial/ |  | SQL practice log with solved queries | Complete 45-50 SQL problems; solve 2 medium problems in <25 minutes each |  | 2026-03-06 |  | Completed | 100
3 | Python for Data Engineering refresh | Practice Prep | 09-06-2026 | 15-06-2026 | Practice Python scripts for file handling, JSON parsing, API ingestion, functions, exceptions, logging, modular code. | https://www.hackerrank.com/domains/python ¦ https://github.com/DataTalksClub/data-engineering-zoomcamp ¦ https://pynative.com/python-file-handling-exercises/ ¦ https://www.youtube.com/watch?v=T23Bs75F7ZQ |  | Python mini scripts repository | Build API/JSON to cleaned CSV pipeline with error handling |  |  |  | In-Progress | 25 | Have completed File Handling module and also added few extra course links | I think we need to break this section into sub-groups, since post learning the "File Handling" conncepts other part of course track like "API ingestion" I am finding it a bit difficult to learn the concept from the given links.
4 | PySpark transformation and performance basics | Practice Prep | 16-06-2026 | 22-06-2026 | Practice DataFrames, joins, aggregations, partitioning concepts, Spark SQL, schema handling, simple optimization. | https://github.com/DataTalksClub/data-engineering-zoomcamp/tree/main/06-batch |  | Mini PySpark transformation pipeline | CSV/input data transformed using PySpark with joins and aggregations |  |  |  | Not Started
5 | Docker, Postgres and local DE environment | Course / Training Resource | 23-06-2026 | 29-06-2026 | Complete Docker/Postgres setup; run local ingestion; understand containers and reproducible environments. | https://github.com/DataTalksClub/data-engineering-zoomcamp ¦ https://www.youtube.com/playlist?list=PL3MmuxUbc_hJed7dXYoJw8DoCuVHhGEQb |  | Dockerized local ingestion environment | Pipeline runs locally in Docker with clear README |  |  |  | Not Started
6 | Terraform and pipeline orchestration fundamentals | Course / Training Resource | 30-06-2026 | 06-07-2026 | Learn IaC basics; provision simple cloud/local resource conceptually; understand orchestration and backfills. | https://github.com/DataTalksClub/data-engineering-zoomcamp |  | Terraform notes and simple IaC script/template | Can explain state, variables, providers and why IaC matters |  |  |  | Not Started
7 | dbt Fundamentals and analytics engineering | Course / Training Resource | 07-07-2026 | 13-07-2026 | Complete dbt fundamentals; build sources, staging, marts, tests, docs; understand lineage and modular SQL. | https://learn.getdbt.com/learn/course/dbt-fundamentals/welcome-to-dbt-fundamentals-5min/welcome ¦ https://github.com/dbt-labs/dbt-Fundamentals-finished-project |  | dbt project with staging/mart/tests/docs | dbt run and dbt test successful; docs generated |  |  |  | Not Started
8 | Project 1: Batch Lakehouse Pipeline | Project | 14-07-2026 | 20-07-2026 | Build end-to-end batch pipeline: ingestion -> storage -> dbt transform -> curated output; document architecture. | https://github.com/DataTalksClub/data-engineering-zoomcamp ¦ https://github.com/dbt-labs/dbt-Fundamentals-finished-project |  | Project 1 GitHub repo, README, architecture diagram | End-to-end reproducible pipeline with tests and documentation |  |  |  | Not Started
9 | Microsoft Fabric DP-700 learning path: ingestion and lakehouse | Course / Training Resource | 21-07-2026 | 27-07-2026 | Study Fabric ingestion, Lakehouse, OneLake, Data Factory/Dataflows, notebooks and pipeline basics. | https://learn.microsoft.com/en-us/credentials/certifications/fabric-data-engineer-associate/ |  | Fabric notes and hands-on artifacts | Complete relevant Microsoft Learn modules and hands-on labs |  |  |  | Not Started
10 | Microsoft Fabric DP-700 learning path: warehouse, real-time and environment management | Course / Training Resource | 28-07-2026 | 03-08-2026 | Study Fabric Warehouse, Real-Time Intelligence, KQL basics, monitoring, optimization and workspace management. | https://learn.microsoft.com/en-us/credentials/certifications/fabric-data-engineer-associate/ |  | DP-700 study notes and practice assessment log | Score readiness on Microsoft practice assessment; list gaps |  |  |  | Not Started
11 | Databricks Data Engineer Associate preparation: Lakehouse, Delta, ingestion | Course / Training Resource | 04-08-2026 | 10-08-2026 | Study Databricks Lakehouse, Delta tables, SQL/PySpark ETL, ingestion patterns, incremental processing. | https://www.databricks.com/learn/certification/data-engineer-associate ¦ https://learn.microsoft.com/en-us/credentials/certifications/implementing-data-engineering-solutions-using-azure-databricks/ |  | Databricks hands-on notebooks | Build bronze/silver/gold pipeline in Databricks/Fabric-style pattern |  |  |  | Not Started
12 | Databricks production jobs, governance and Project 1 upgrade | Project | 11-08-2026 | 17-08-2026 | Upgrade Project 1 with Databricks workflow/job, Delta design, governance notes, monitoring and optimization notes. | https://www.databricks.com/learn/certification/data-engineer-associate |  | Updated Project 1 with Databricks workflow | Can explain Delta, Unity Catalog/governance, jobs, retries and optimization |  |  |  | Not Started
13 | Airflow 101: DAGs, scheduling, UI, operators | Course / Training Resource | 18-08-2026 | 24-08-2026 | Complete Airflow basics: DAGs, scheduling, operators, task lifecycle, UI, local dev. | https://academy.astronomer.io/ |  | Airflow learning notes and first DAG | DAG runs successfully locally; tasks visible in UI |  |  |  | Not Started
14 | Airflow production patterns: retries, sensors, variables, debugging | Course / Training Resource | 25-08-2026 | 31-08-2026 | Practice retries, sensors, variables, connections, XCom basics, failure handling and debugging. | https://academy.astronomer.io/ |  | Airflow production-pattern DAG | DAG includes retries, logging, schedule, and basic failure handling |  |  |  | Not Started
15 | Project 2: Orchestrated production data pipeline | Project | 01-09-2026 | 07-09-2026 | Build pipeline orchestrated by Airflow: ingest -> transform -> validate -> publish; integrate dbt if possible. | https://academy.astronomer.io/ ¦ https://learn.getdbt.com/learn/course/dbt-fundamentals/welcome-to-dbt-fundamentals-5min/welcome |  | Project 2 GitHub repo and architecture diagram | Pipeline handles retry/backfill scenario and is well documented |  |  |  | Not Started
16 | Project 2 hardening: CI/CD, data quality and observability | Project | 08-09-2026 | 14-09-2026 | Add GitHub Actions/linting/test simulation, data quality checks, logging, failure playbook and README improvements. | https://github.com/DataTalksClub/data-engineering-zoomcamp |  | Production-readiness checklist for Project 2 | Can explain deployment, testing, monitoring, backfill and incident handling |  |  |  | Not Started
17 | Kafka fundamentals: topics, partitions, producers, consumers | Course / Training Resource | 15-09-2026 | 21-09-2026 | Learn Kafka fundamentals and event-streaming concepts; practice producer/consumer locally if possible. | https://www.confluent.io/training/ ¦ https://github.com/confluentinc/learn-kafka-courses |  | Kafka notes and simple producer/consumer | Can explain topics, partitions, offsets, consumer groups and schema registry basics |  |  |  | Not Started
18 | Streaming design: schema evolution, late data, idempotency | Practice Prep | 22-09-2026 | 28-09-2026 | Practice streaming architecture decisions; document batch vs streaming trade-offs, idempotency and late-arriving data handling. | https://www.confluent.io/training/ ¦ https://github.com/DataTalksClub/data-engineering-zoomcamp/tree/main/07-streaming |  | Streaming design notes | One design note comparing batch, micro-batch and streaming choices |  |  |  | Not Started
19 | Project 3: Hybrid batch + streaming data platform | Project | 29-09-2026 | 05-10-2026 | Build/outline Kafka -> Spark/consumer -> lakehouse/warehouse -> curated layer -> dashboard. | https://github.com/DataTalksClub/data-engineering-zoomcamp/tree/main/07-streaming ¦ https://www.confluent.io/training/ |  | Project 3 repo/design and working POC | Working POC or strong architecture with code stubs, README and trade-offs |  |  |  | Not Started
20 | Project 3 dashboard and executive storytelling | Project | 06-10-2026 | 12-10-2026 | Add Power BI/BI dashboard, architecture diagram, business narrative, cost/performance notes and limitations. | https://learn.microsoft.com/en-us/training/powerplatform/power-bi ¦ https://github.com/DataTalksClub/data-engineering-zoomcamp |  | Portfolio-ready Project 3 | Project can be explained in 5 minutes for an interview |  |  |  | Not Started
21 | Google Cloud Professional Data Engineer path: foundations and BigQuery | Course / Training Resource | 13-10-2026 | 19-10-2026 | Start Google Data Engineer path: IAM basics, Cloud Storage, BigQuery, data warehouse/lake design. | https://www.skills.google/paths/16 ¦ https://cloud.google.com/learn/training/data-engineering-and-analytics |  | GCP notes and BigQuery lab outputs | Complete initial GCP data engineer path activities/labs |  |  |  | Not Started
22 | Google Cloud PDE: Dataflow, Pub/Sub, Composer and streaming analytics | Course / Training Resource | 20-10-2026 | 26-10-2026 | Study batch pipelines, streaming analytics, Dataflow, Pub/Sub, Composer/Airflow concepts and automation. | https://www.skills.google/paths/16 ¦ https://cloud.google.com/learn/certification/data-engineer |  | GCP service mapping and lab notes | Can map Azure/Fabric/Databricks services to GCP equivalents |  |  |  | Not Started
23 | Interview prep: SQL, Python, DE system design | Practice Prep | 27-10-2026 | 02-11-2026 | Daily interview prep: SQL 50 review, Python ETL problems, DE system design drills, pipeline whiteboarding. | https://leetcode.com/studyplan/top-sql-50/ ¦ https://grow.google/interview-warmup-archived |  | Interview question bank and mock notes | Complete 3 mock system designs and repeat SQL/Python weak areas |  |  |  | Not Started
24 | Final portfolio, resume and application sprint | Project | 03-11-2026 | 09-11-2026 | Finalize GitHub, LinkedIn/resume, project one-pagers, certification plan, target job list and application tracker. | https://careers.microsoft.com/v2/global/en/hiring-tips/interview-tips.html ¦ https://grow.google/interview-warmup-archived |  | Final portfolio and job application tracker | 3 polished projects, resume updated, 20 target roles shortlisted |  |  |  | Not Started

## Plan Summary
Metric | Value
Plan Start Date | 26-05-2026
Plan End Date | 09-11-2026
Duration | 24 weeks / 6 months
Primary Role Target | Microsoft-first Data Engineering roles
Secondary Role Target | Google Cloud / multi-cloud data engineering roles
Recommended Weekly Effort | 15-18 hours/week
Portfolio Target | 3 projects: Batch Lakehouse, Orchestrated Pipeline, Hybrid Streaming Platform
Certifications Target | DP-700, Databricks Data Engineer Associate, Google Professional Data Engineer (optional in 6 months; continue if needed)